# Notes from Informal Steering Group Meeting

Date: June 9th, 2016

Present: Susan Daenke, Roger Evans, Alex Reid, Diane Bohm, Mike Finbow, Patsy Parsons (on invitation)

Absent: Eric Bohm, Yasmin Orcay

# Main Issues Arising from Cherwell Council Comments on Draft Plan

(TASKS AGREED)

1. SEA: Mike to work on and to apply for a screening assessment. See Southfield Farm Application for format

2. Greenbelt: DB and RE to work on this issue. DB to find framework from CPRE

3. Objectives vs Policies chapter – Patsy to re-organise

4. Chapter 1,2,3, - Susan to re-draft

5. Copyright, permissions for photos – Alex and Yasemin (Alex to ask)

6. Priories for Parish Council – RE to pull out of our work to use at our combined meeting

7. Design Code – MF to sent new draft to Cherwell

We aim to have our draft ready for Cherwell by the end of July.

# DEADLINE FOR THIS WORK: JUNE 25TH - TO DIANE

Diane:

Follow up with Bob:

Duchy of Cornwall contact regarding Gallosbrook Way

Contact for : Natural England and Environment Agency

RE and DB to meet with Christine Cherry from Cherwell and John Broad from CPRE on Tuesday, June 14th, 2016.

# Verges – it has come to our attention that Mr. Treadwell has permission to put wooden bollards on his verge. It is time to address the verge issue in the village.

DB – June 13th