## schedule
Sample Payment & Garage Conversion Project Schedule
( cross out / sign as paid )
Job : A Garage Conversion
| Stage | Draft Date ( +/- 7 to 10 days ) | Est Date ( w/c) +/- 7 days | To A Young's Extension & Construction Services Ltd | TO Bricklayer | To Martin Gale | To carpenter | To plumber | Other ? |  |  |  | TOTAL | Tradesmen Own | Dates agreed | Materials / Eqpt | Date Scheduled | B / Regs Visit | Other Notes
1 | 1a) Letter In To B / control , 1b) H&S : 1st aid b / acc book/sign/fence/Clear safe 5w&h all) , 2) Go Ahead Letter from customer ,3) Pre site meeting with customer 3a) agree / measure windows & doors + source bricks , 4) Discuss / Copy of schedule / plans + hse / pad keys to team 5) agree draft dates all team , 6) Line up all mat / eqpt 7) spare keys cut |  | 2weeks before | [9 empty] | 0 | [6 empty] | ALL TOO LONG ! / NEED TO > TIGHT! & POSS > MG DAYS / CLEAR 5W& H TO ELL / HOW ETC !!!
2 | Site set up ( sec fence up / sign / ply for skip etc & agree materials location ( Mh 1st !) , ? dry / safe storage ? !) From store / 1A = , From 27N = , From Merchants = , SKIP IN , initial building control meeting , Identify / confirm situation + mark plans re ; services runs to avoid & lintel over ( E , W , S ,G , Tel) , new sewer run < > mat in ( br ok) + lintel over , r/water run , floor joist / bearer location , roof plate ? Id / mark up on plans & site : Exact dimensions of extension ( for b&b order etc ) , foundation / footing structure , inside FFL ( -75 screed/70 insul & 155 Beams ( 300 total ) = bottom B&B beams / top inner footings , - further 225 ( 525 < ffl total ) void = level of scrape out to ! etc Cladding stop ? , window sizes ? , Review all plans / no ? |  | day 1 | [9 empty] | 0 |  |  | SKIP , SEC FENCE , INIT MATERIALS UP TO screed |  | BR INIT VISIT FRI 27/3
3 | New waste / sewer rus to mh ( br ok so can cover ) & cut out / do any foundations / dwarf wall lintel work |  | day 1 | [9 empty] | 0 |  |  |  |  | BR OK SEWER RUN / lintel ?
4 | Footings done to dpc & any internal block wall footings done to dpc |  | day 2 | [9 empty] | 0 |  |  |  |  | BR OK DPC
| bricks removed & finished floor level set with laser ! , so garage conversion same finished fl.oor level as main house . |  | day 2 | [9 empty] | 0
| Garage door removed , Floor Damp membrane , insualtion & reinforced screed |  | day 3-4 | [9 empty] | 0
| 1ST STAGE PAYMENT | [11 empty] | 0
6 | Front dwarf wall toothed out & built |  | day 4- 5 | [9 empty] | 0
14 | new external windows / doors in |  | day 6 | [9 empty] | 0
15 | new openings to house cut & lintels instaled |  | day 6 - 7 | [9 empty] | 0 |  |  |  |  | BR OK
| New insulated internal studowrk & block walls built |  | day 7 - 9 | [9 empty] | 0 |  |  |  |  | Br OK
12 | Ceiling insualted / counter batoned |  | day 7-9 | [9 empty] | 0
17 | 1st fix elec ( incl new f/box & x/fan if required ) & plumb ( h/c to cloak sink & loo + sink / loo waste ) |  | day 9-10 | [9 empty] | 0
19 | 1st fix carp w boards / door linnings / boxing |  | day 9-10 | [9 empty] | 0
| 2nD STAGE PAYEMNT | [11 empty] | 0
| Walls & Ceiling plasterboarded |  | day 11
| Plasterwork |  | day 12
22 | 2nd fix plumb ( plumb in cloak ) , elec & carp | W/C 06/08+ W/C 13/08 | day 13 -14 | [9 empty] | 0
23 | Decorating if required |  | ? | [9 empty] | 0
24 | CONTINGENCY |  | day 15 | [9 empty] | 0
25 | snags / extra's ( decorating , tiling etc ) completion / site cleared | END W/C 13/08 | day 15 | [9 empty] | 0 |  |  |  |  | BR FINAL & Elec Certificate
| FINAL PAYMENT + ANY EXTRA'S AGREED | [11 empty] | 0
SUB TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
gauranteed agreed
zero control
A Young's Direct Transfer To Bank Please within few days of invoice / STAGE BEING MET
| BANK : Lloyds tsb , biggleswade , sort code 309079 , acct 1638036 | [13 empty] | 23950
Agreed extra's
| Stage | Draft Date ( +/- 7 to 10 days ) | Est Date ( w/c) +/- 7 days | To A Young's Extension & Construction Services Ltd | TO Bricklayer | To Martin Gale | To carpenter | To plumber | Other ? |  |  |  | TOTAL
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | W/C 16/07 + W/C 23/07 | [10 empty] | 0
|  | W/C 06/08+ W/C 13/08 | [10 empty] | 0
|  | END W/C 13/08 | [10 empty] | 0
0
SUB TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0